# Latency plan — what shipped, what did not, and why

5 September 2026 · Project Vaani · all five agents

An audit of every item in 25-latency-plan-2026-09-05, against what is actually

running. Nothing here is claimed without a measurement or a stated reason.

────────────────────────────────────────

# Result

Per-turn latency on a real call: 1,096 ms → 877 ms (p50).

Measured on wf2, run 392 before against run 776 after, 14 turns.

|  | run 392 | run 776 |
| --- | --- | --- |
| p50 TOTAL | 1.096 s | 0.877 s |
| endpoint (mean) | 0.523 | 0.473 |
| LLM | 0.527 | 0.351 |
| TTS first audio | 0.069 | 0.106 |

TTS first-audio rising while TOTAL falls is the signature of token streaming

working: it now covers a short opening chunk instead of being clocked from a

whole buffered sentence, so it measures less of the turn than before.

Run 776 also completed a full qualification — property type, bill (15,000),

location, roof, name, and a decision — so the speed did not cost the outcome.

────────────────────────────────────────

# Phase 0 — COMPLETE

| Item | Status | Evidence |
| --- | --- | --- |
| 0a stt_finalisation_budget_secs 0.45 → 0.2 | No-op. Already 0.2 on all five. | The 250 ms "dead timer" is max(0, 0.2−0.2) = 0. It never existed. No saving claimed. |
| 0b Cartesia token streaming | SHIPPED, verified, now DEFAULT | Run 776. DEFAULT_TTS_TOKEN_STREAMING = True, enabled on all five |
| 0c llm_hedge 2 → 3 | SHIPPED on all five | Measured wf3, 3 runs each way: 1.42/1.31/1.43 vs 1.34/1.35/1.40 — ~50 ms, inside noise. Not the 328 ms the old bench claimed. Kept because it is the code's own default and the tail is better; no p50 win claimed. |

────────────────────────────────────────

# Phase 1 — COMPLETE, and it immediately changed a conclusion

text_aggregation_secs now persists in rtf-latency-breakdown, and

tools/vaani_runs.py prints the endpoint distribution and any unaccounted time.

The first thing it showed, on run 776:

endpoint spread: min 0.378  p50 0.390  max 1.139   under 0.6s: 13/14

The endpoint p50 is 0.390 s, not the 0.523 s mean quoted all week. The mean

was dragged up entirely by turn 1. Thirteen of fourteen turns were under 0.6 s.

That reframes the remaining gap: **at p50 the server side is 877 ms against an

800 ms budget — 77 ms over, not 319 ms.** Most of the endpoint work the plan

contemplated is aimed at a problem that is smaller than the mean implied.

Turn 1 is the outlier (endpoint 1.139 s). That is not the cold prompt cache —

prewarm.py already handles the LLM side and turn 1's LLM was a normal 0.488 s.

It is MIN_CONFIDENT_TURN_S = 0.65: a one-word "హలో" is shorter than that, so

the detector demands near-certainty (0.995) before ending the turn. That is the

rule that stops callers being cut off mid-sentence. **It is a deliberate safety

cost on the shortest utterance, not a defect.**

────────────────────────────────────────

# Phase 2

## 2b — Two landmines. SHIPPED.

`PartialResponder` pushed the promoted transcript UPSTREAM, toward the

STT, where nothing consumes it — and set _promoted, suppressing the genuine

final. Fixed to always push DOWNSTREAM.

Speculation now FAILS CLOSED. It generated from

compose_system_prompt_for_node with get_state_block=lambda: "" — a hit

would have spoken a reply with no answer-first rule, no two-ask cap and no

repeat guard. It now refuses to build; the call site catches and logs.

## 2a — Realtime STT. ATTEMPTED, BROKE PRODUCTION, REVERTED.

Switched to saaras:v3-realtime. Runs 779 and 780 immediately after:

| run | result |
| --- | --- |
| 779 | captured nothing — no variables, no nodes visited |
| 780 | p50 3.573 s, one turn at 5.150 s, LLM alone 3.668 s |

Run 780's user transcript is the word "హలో" repeated twenty-two times. The

caller said it once. The realtime model emits a partial per fragment; each was

becoming its own turn, and the LLM was re-reading a context full of duplicates.

The ordering in the plan was right and my reasoning about it was wrong. 2b

before 2a was correct — but before that fix, PartialResponder pushed upstream

into a dead end. It was harmless because it was broken. Fixing it made it

live, in the same session that first gave it partials to act on. Two changes

each defensible alone; together they turned every partial into a turn.

Reverted with set_stt_config.py --model "saarika:v2.5" --apply. With no

interims the partial path is inert again, so the code fix is harmless where it

sits.

Before this is attempted again, all three must hold:

PartialResponder must promote at most once per turn. Its logic assumes

an STT emitting one final, not twenty partials.

SarvamRealtimeSTTService sets frame.finalized = True, opening a different

branch in TurnAnalyzerUserTurnStopStrategy._handle_transcription. Unexamined,

and a second candidate for the 22 turns.

It cannot be piloted. STT is an ORGANISATION-level setting, not

per-workflow — the plan assumed otherwise. Any retry moves all five agents at

once, so it needs a test call booked in advance and an immediate revert ready.

## 2c — LLM turn completion. NOT DONE. BLOCKED BY 2a.

The architecture from the client's transcript — the LLM polled while the caller

is still speaking, emitting ✓ / ○ / ◐ instead of a reply — requires interim

transcripts to poll against. saarika:v2.5 emits none. **2c cannot be built

until 2a works.** Building it now would produce untestable code sitting behind a

switch that is off.

## 2d — Throttle the detector's CPU. NOT DONE, and RECOMMENDED AGAINST for now.

_probability() costs ~5–7 ms and runs on every 20 ms frame during silence —

~53 ms per turn of event-loop occupancy. The plan already said this is a

concurrency win, not a p50 win.

Phase 1 removed most of its remaining case: the endpoint p50 is 0.390 s, which

is close to its 250 ms budget, and current call volume is a handful per day, so

event-loop contention is not the binding constraint. It touches the one

component that stops callers being cut off. **Marginal benefit against real

risk — not worth doing now.** Revisit when concurrent call volume rises.

────────────────────────────────────────

# Where the remaining 77 ms sits

At p50, on a real call: endpoint 0.390 + LLM ~0.35 + TTS ~0.106 ≈ 0.85 s against

the 800 ms budget.

TTS is 106 ms against a 190 ms budget — under, nothing to win.

Endpoint is 390 ms against 250 ms. Closing it means the realtime STT path

(2a) or a faster detector verdict — and the repo's own sweep shows deciding

earlier makes calls slower on average and spends against the 2 %

false-interruption floor.

LLM is ~350 ms against 200 ms. Closing it needs a non-reasoning model,

which this Groq account does not offer, or 2c.

Both remaining routes run through 2a. That is the honest bottleneck.

# And the number that does not move

telephony_overhead_ms: 490, marked "NOT engineerable" in

latency_budget.yaml. At the measured 877 ms the caller hears about 1.37 s.

At a perfect 800 ms they would hear 1.29 s. **700 ms at the caller's ear is not

available on a phone line**, and no amount of the work above changes that.

────────────────────────────────────────

# Regression — nothing destroyed

Checked after every change, by diffing the failure list before and after:

414 tests pass, zero new failures. The 10 failures in

test_vaani_filler_cover are pre-existing and fail identically with every

change reverted.

vaani_eval wf2: 18/25, 9 hard — twice, identical.

Behaviour probes on all five agents: answers the caller's question, then asks

its own; answers off-topic questions; remembers across turns; no false repair

lines.

Two suites can only run in CI on this machine: test_partial_response.py needs

pytest-asyncio and the Cartesia factory tests need google.genai. Neither is

installed here, and that gap is part of why the 2a failure was not caught before

a live call.