# Speech Recognition Customization Workstream

# Project Vaani — Telugu ASR Ownership Plan

| Field | Value |
| --- | --- |
| Document ID | STT-001 |
| Version | 1.0 |
| Date | 2026-08-23 |
| Status | Draft |
| Preceding documents | FS-001 §3.3, SRS-001, HLD-001 ADR-04, LLD-001 §1.2, TP-001 §7.2 |
| Workstream owner | Engineering |

────────────────────────────────────────

# 1. Why this workstream exists

FS-001 concluded that the entire justification for building this platform is control,

and that the most valuable form of that control is ownership of the speech recognition

layer. The originating complaint was blunt and correct:

"for Telugu all are trash"

That is a true statement about generic Telugu ASR. It is not a permanent condition.

It is a solvable engineering problem, and it is solvable only by owning the pipeline.

On Vapi or Dograh it is unsolvable at any price, because neither lets you replace or

train the recognition model.

This document turns that from a paragraph in a feasibility study into a planned

workstream with requirements, a data pipeline, an evaluation method, effort estimates and

risks.

## 1.1 Why Telugu ASR fails on these calls specifically

Four compounding causes, each with a different remedy:

| # | Cause | Remedy | Level |
| --- | --- | --- | --- |
| C1 | Generic models are trained on read/broadcast speech, not spontaneous telephone speech | Domain fine-tuning | 3 |
| C2 | Entities — customer names, city names, amounts, product terms — are rare tokens the model has barely seen | Vocabulary boost, then entity-dense training | 1 → 3 |
| C3 | Telephone audio is 8 kHz, narrowband, noisy, often speakerphone | Train on real call audio at real bandwidth | 3 |
| C4 | Code-mixing — Telugu with English loanwords (loan, EMI, subsidy, interest) | Mixed-script training data | 3 |

C2 is the highest-leverage. Overall word error rate can look acceptable while the words that actually decide the call outcome — whose name, which city, how much — are wrong. Published Indic ASR work reports the gap concentrates precisely on entity-dense audio, which matches what these calls show.

────────────────────────────────────────

# 2. The Four-Level Ladder

Levels are cumulative and independently valuable. **Each level ships and is measured on

its own** — the workstream is not a single bet on level 3.

| Level | Capability | Release | Marginal STT cost | Effort |
| --- | --- | --- | --- | --- |
| L0 | Measure — corpus, baseline, entity metric | v1, Phase 1 | — | 6 d |
| L1 | Tune — vocabulary boost, provider selection | v1 | unchanged | 4 d |
| L2 | Correct — LLM transcript repair, engine racing | v1 | small increase | 7 d |
| L3 | Own — self-hosted fine-tuned IndicConformer | v2 | → near zero | 28 d |

L0  measure ──▶ L1  tune ──▶ L2  correct ──▶ L3  own

│              │            │               │

WER +          keyword      LLM repair     fine-tuned

entity         boost        + racing       IndicConformer

baseline                                   on your own audio

│              │            │               │

└──── every level judged against the L0 baseline ────┘

Design rule: every level plugs into the same SttPort interface (LLD §1.2). No level

requires changes to any other module. That is the whole point of ADR-04.

────────────────────────────────────────

# 3. Requirements

New requirements, to be merged into SRS-001 §3.2 and §4.2.

## 3.1 Functional

| ID | Requirement | Priority | Release |
| --- | --- | --- | --- |
| FR-STT-01 | The system shall maintain a held-out Telugu evaluation corpus of real call audio with human-verified reference transcripts. | M | v1 |
| FR-STT-02 | The system shall compute and report Word Error Rate against that corpus for any configured STT implementation. | M | v1 |
| FR-STT-03 | The system shall compute and report entity accuracy separately from WER, over a defined entity list (person names, place names, monetary amounts, product terms). | M | v1 |
| FR-STT-04 | The system shall support supplying a per-agent vocabulary/keyword-boost list to STT implementations that accept one, and shall degrade cleanly where they do not. | M | v1 |
| FR-STT-05 | The system shall support an optional transcript correction stage between STT and the Brain, configurable per agent, with a bounded latency budget. | S | v1 |
| FR-STT-06 | The correction stage shall be a no-op when disabled and shall never increase turn latency beyond its configured budget. | M | v1 |
| FR-STT-07 | The system shall support dispatching one audio stream to two STT implementations concurrently and selecting a result by confidence and/or arrival order. | C | v2 |
| FR-STT-08 | The system shall support an STT implementation backed by a self-hosted model server reachable over HTTP/WebSocket. | M | v1 |
| FR-STT-09 | The system shall export a training corpus of call audio and transcripts, restricted to recordings where training_use_permitted is true. | M | v1 |
| FR-STT-10 | The training export shall exclude or mask personal data not required for acoustic training, per the consent basis recorded. | M | v1 |
| FR-STT-11 | The system shall support A/B routing of live calls between two STT implementations at a configurable ratio. | S | v2 |
| FR-STT-12 | The system shall record, per turn, which STT implementation and model version produced the transcript. | M | v1 |

FR-STT-08, FR-STT-09 and FR-STT-12 are the v1 obligations that make level 3 possible later. If v1 ships without them, level 3 is not merely deferred — it is blocked behind a retrofit. This is the single most important scheduling point in this document.

## 3.2 Non-functional

| ID | Requirement | Target |
| --- | --- | --- |
| NFR-STT-01 | WER on the held-out corpus, L1 | ≤ L0 baseline |
| NFR-STT-02 | WER on the held-out corpus, L2 | < L0 baseline |
| NFR-STT-03 | WER on the held-out corpus, L3 | materially better than baseline — target set after L0 |
| NFR-STT-04 | Entity accuracy, L3 | primary success metric — target set after L0 |
| NFR-STT-05 | Correction stage added latency | ≤ 120 ms p95 |
| NFR-STT-06 | Self-hosted model server STT latency | ≤ hosted provider p95 |
| NFR-STT-07 | Model server availability during calls | ≥ hosted provider, with automatic failover to a hosted STT |
| NFR-STT-08 | Corpus size for L3 training | ≥ 20 hours verified, ≥ 100 hours weakly-labelled (working assumption, revised at L0) |

No numeric WER target is asserted for NFR-STT-03/04. Setting one before the baseline exists would be fabrication. The targets are defined as an output of L0 and approved before L3 work begins.

────────────────────────────────────────

# 4. Level 0 — Measure (v1, Phase 1)

Nothing else in this workstream can be judged without this. It is also already

required by TP-001 as TPR-1/TPR-2, so it is shared work, not additional work.

## 4.1 Corpus construction

MinIO recordings

│

▼

┌─────────────────┐   training_use_permitted = true only  (FR-CMP-04)

│  Consent filter │

└────────┬────────┘

▼

┌─────────────────┐   VAD split into utterances; drop bot channel

│  Segmentation   │

└────────┬────────┘

▼

┌─────────────────┐   stratify: vertical × dialect × audio quality × entity density

│   Sampling      │

└────────┬────────┘

▼

┌─────────────────┐   best available ASR draft, then HUMAN correction

│  Transcription  │

└────────┬────────┘

▼

┌─────────────────┐   frozen; never used for training  ← critical

│ HELD-OUT SET    │

└─────────────────┘

Held-out discipline. The evaluation set is frozen and never enters training. A model

evaluated on data it trained on will look excellent and perform badly on real calls. This

is the most common way ASR projects fool themselves.

## 4.2 Corpus specification

| Property | Target |
| --- | --- |
| Held-out evaluation set | 2–3 hours, human-verified |
| Utterance count | ≥ 1,000 |
| Coverage | All live verticals |
| Audio conditions | Include speakerphone, poor network, background noise — deliberately, not by accident |
| Entity annotation | Names, cities, amounts, product terms marked |
| Reference format | Verbatim, including code-mixed English tokens as spoken |

## 4.3 Metrics

| Metric | Definition |
| --- | --- |
| WER | Standard word error rate, normalised for punctuation and casing |
| Entity accuracy | Correctly recognised annotated entities ÷ total annotated entities |
| CER | Character error rate — more informative than WER for agglutinative Telugu |
| Per-condition WER | Broken out by audio condition, so a good average cannot hide a bad case |
| Latency | STT finalisation time, per implementation |

CER is included deliberately. Telugu is agglutinative; a single wrong morpheme marks a whole word wrong under WER, which overstates degradation and understates improvement. CER tracks real progress more honestly.

## 4.4 Baseline capture

Measure the current Dograh stack on this corpus before anything is built. Every later

"better" or "parity" claim references this recorded number, not memory.

## 4.5 Deliverables

Frozen held-out corpus with verified transcripts and entity annotations

Baseline report: WER, CER, entity accuracy, per-condition breakdown

Reusable benchmark harness (stt_bench.py)

Approved numeric targets for NFR-STT-03 and NFR-STT-04

────────────────────────────────────────

# 5. Level 1 — Tune (v1)

Cheap, immediate, no infrastructure.

## 5.1 Vocabulary boosting

Per-agent keyword lists supplied to the STT where supported (FR-STT-04):

| Category | Examples |
| --- | --- |
| Product terms | లోన్, ఈఎంఐ, వడ్డీ, సబ్సిడీ, సోలార్, ప్యానెల్ |
| Amount forms | లక్ష, వేల, కోటి |
| Cities | vertical-specific place-name lists |
| Company / agent names | BS Wealth, శ్రేయ, దీప్తి |
| Code-mixed English | loan, EMI, interest, subsidy, tenure |

The SttCapabilities declaration (LLD §1.2) governs behaviour: implementations without

boost support ignore the list, and the capability is recorded so evaluation can attribute

results correctly.

## 5.2 Provider selection

Evaluate available Telugu-capable STT providers against the L0 corpus and pick on

evidence rather than reputation. Reuse compare_models.py.

## 5.3 Deliverables

Vocabulary lists per agent, in the agent artefact (stt.vocabulary)

Provider comparison report against the L0 corpus

L1 measurement vs baseline

────────────────────────────────────────

# 6. Level 2 — Correct (v1 correction, v2 racing)

## 6.1 Transcript correction

A small, fast model repairs the transcript before the Brain sees it.

raw transcript ──▶ Corrector ──▶ corrected ──▶ Brain

│

bounded: ≤120 ms p95, else pass through unchanged

| Design point | Decision |
| --- | --- |
| Model | Small/fast; correction is not reasoning |
| Prompt | Domain glossary + entity list; instruct minimal edits only |
| Budget | Hard timeout; on expiry the raw transcript passes through (FR-STT-06) |
| Safety | Corrector may never introduce content absent from the audio — measured as a hallucination rate |
| Observability | Both raw and corrected text stored on the turn record |

The hallucination guard matters more than the accuracy gain. A corrector that invents a plausible amount or name is far worse than one that leaves a garbled word alone. Both versions are stored so this is auditable rather than assumed.

## 6.2 Engine racing (v2)

Dispatch one stream to two engines; select by confidence, with arrival order as

tie-breaker (FR-STT-07). STT is a small fraction of per-call cost, so paying twice for it

is usually rational.

Composite RacingStt satisfies the same SttPort — no other module changes.

## 6.3 Deliverables

TranscriptCorrector with bounded budget and pass-through fallback

Hallucination-rate measurement

L2 measurement vs baseline

(v2) RacingStt composite

────────────────────────────────────────

# 7. Level 3 — Own (v2)

Self-hosted, fine-tuned Telugu ASR. This is the level that makes the capability

permanent and drives marginal STT cost toward zero.

## 7.1 Base model

AI4Bharat IndicConformer — hybrid CTC-RNNT conformer, all 22 official Indian

languages, MIT licensed (commercial use permitted), fine-tunable via AI4Bharat NeMo.

| Property | Value |
| --- | --- |
| Licence | MIT — no commercial restriction |
| Languages | 22, including Telugu |
| Architecture | Hybrid CTC + RNNT |
| Fine-tuning | Supported, tooling published |
| Deployment | Self-hosted; GPU for training, CPU/GPU for inference |

Alternatives (Whisper-family, other Indic models) are evaluated at L0 as baselines. IndicConformer is the planned base because of licence, Telugu nativeness and fine-tuning support together — not any one of those alone.

## 7.2 Training data pipeline

Consented recordings          Synthetic entity-dense audio

(real, weakly labelled)       (TTS-generated, exactly labelled)

│                              │

├──── human-verified subset    │

│                              │

▼                              ▼

┌──────────────────────────────────────────┐

│            Training corpus                │

│   real spontaneous speech + entity mass   │

└────────────────────┬─────────────────────┘

▼

Fine-tune IndicConformer

▼

Evaluate on FROZEN L0 held-out set

Why synthetic data is in the plan. Real recordings supply authentic telephone

acoustics and spontaneous speech, but they under-represent the rare tokens that matter —

each customer name appears once. Published work indicates the Indic ASR gap closes

substantially when training data is deliberately entity-dense. Generating TTS audio

over your real name/city/amount/product lists produces exactly-labelled, entity-saturated

data cheaply, and combining it with real audio addresses C2 and C4 together.

Neither source alone is sufficient: synthetic-only produces a model that fails on real

telephone acoustics; real-only produces a model that still misses entities.

## 7.3 Data governance — gating condition

| Requirement | Detail |
| --- | --- |
| Consent | Only training_use_permitted = true recordings (FR-CMP-04, FR-STT-09) |
| Secondary purpose | ASR training is a secondary processing purpose and must be covered by the consent obtained — this is FS-001 open item OI-4 |
| Minimisation | Export excludes personal data not needed for acoustic training (FR-STT-10) |
| Storage | Training corpora held under the same retention controls as recordings |
| Deletion | A deletion request must remove source audio from the corpus; retraining is not required retrospectively but the corpus must not be reused |

OI-4 gates L3 entirely. No training may begin until the consent basis is confirmed in writing. L0/L1/L2 are unaffected — they process audio for the call's own purpose.

## 7.4 Training approach

| Aspect | Plan |
| --- | --- |
| Compute | Rented GPU hours, not owned hardware |
| Strategy | Fine-tune from the multilingual checkpoint; do not train from scratch |
| Curriculum | Real verified data first, then synthetic entity augmentation, then mixed |
| Validation | A validation split distinct from both training and the frozen held-out set |
| Versioning | Every model version tagged, with its training corpus manifest recorded |
| Stop criterion | Improvement on the held-out set, not on training loss |

## 7.5 Serving

Session Worker ──▶ SelfHostedStt ──▶ Model Server ──▶ fine-tuned IndicConformer

│                                    │

└── automatic failover ──▶ hosted STT provider  (NFR-STT-07)

| Concern | Design |
| --- | --- |
| Interface | SelfHostedStt implements SttPort (FR-STT-08); nothing else changes |
| Failover | Model server unavailable or slow → hosted provider, automatically, logged |
| Rollout | A/B at a configurable ratio (FR-STT-11), starting low |
| Attribution | Every turn records the implementation and model version (FR-STT-12) |
| Rollback | Configuration change; ≤5 min, same mechanism as agent rollback |

Automatic failover to a paid hosted provider is deliberate. A self-hosted model must never be able to take down live client campaigns; that would trade a quality problem for an availability problem.

## 7.6 Deliverables

Training corpus export tooling (consent-filtered)

Synthetic entity-dense generation tooling

Fine-tuning pipeline and model registry

Model server + SelfHostedStt adapter

A/B routing and failover

L3 evaluation vs baseline and vs L2

────────────────────────────────────────

# 8. Work Breakdown

Appended to PMP-001 as WBS 9. Effort in engineering-days, same basis and uncertainty

as PMP §3.

## WBS 9.1 — Level 0 (v1, Phase 1)

| ID | Package | Days | Notes |
| --- | --- | --- | --- |
| 9.1.1 | Consent-filtered export from MinIO | 1 | Also serves FR-STT-09 |
| 9.1.2 | Segmentation and stratified sampling | 1 |  |
| 9.1.3 | Draft transcription + human verification | 3 | The slow part; largely manual |
| 9.1.4 | Entity annotation and entity list | 1 |  |
| 9.1.5 | Benchmark harness (WER / CER / entity / per-condition) | 2 |  |
| 9.1.6 | Dograh baseline capture | 1 |  |
|  | Subtotal | 9 | Overlaps TP-001 TPR-1/TPR-2 — ~6 d is shared, not additional |

## WBS 9.2 — Level 1 (v1)

| ID | Package | Days |
| --- | --- | --- |
| 9.2.1 | Vocabulary boost plumbing + capability degradation | 2 |
| 9.2.2 | Per-agent vocabulary lists | 1 |
| 9.2.3 | Provider comparison against L0 corpus | 2 |
|  | Subtotal | 5 |

## WBS 9.3 — Level 2

| ID | Package | Days | Release |
| --- | --- | --- | --- |
| 9.3.1 | TranscriptCorrector with bounded budget + pass-through | 3 | v1 |
| 9.3.2 | Hallucination-rate measurement | 1 | v1 |
| 9.3.3 | Raw + corrected storage on turn record | 1 | v1 |
| 9.3.4 | RacingStt composite | 3 | v2 |
|  | Subtotal | 8 (5 in v1) |  |

## WBS 9.4 — Level 3 (v2)

| ID | Package | Days |
| --- | --- | --- |
| 9.4.1 | Training corpus export at scale | 2 |
| 9.4.2 | Synthetic entity-dense audio generation | 4 |
| 9.4.3 | NeMo fine-tuning pipeline setup | 4 |
| 9.4.4 | Training runs and iteration | 8 |
| 9.4.5 | Model registry and versioning | 2 |
| 9.4.6 | Model server deployment | 4 |
| 9.4.7 | SelfHostedStt adapter + failover | 3 |
| 9.4.8 | A/B routing and canary rollout | 3 |
| 9.4.9 | L3 evaluation and sign-off | 2 |
|  | Subtotal | 32 |

## 8.1 Summary and effect on the programme

| Level | Days | Release | In v1 critical path? |
| --- | --- | --- | --- |
| L0 | 9 (≈3 net of TP overlap) | v1 Phase 1 | Yes — gates G4 |
| L1 | 5 | v1 | Yes |
| L2 | 5 of 8 | v1 | Partly |
| L3 | 32 | v2 | No |
|  | ~13 net added to v1 |  |  |
|  | 35 for v2 (L2 racing + L3) |  |  |

Revised PMP totals:

|  | Before | After |
| --- | --- | --- |
| v1 effort | 133 d | ~146 d |
| v1 with 30% contingency | ~173 d | ~190 d |
| v2 STT workstream | (unplanned) | 35 d, now planned |

## 8.2 The one decision you can overrule

L3 is planned as v2 and deliberately kept off the v1 critical path.

|  | If L3 stays v2 (recommended) | If L3 moves into v1 |
| --- | --- | --- |
| v1 ships | ~146 d | ~178 d |
| v1 depends on a model training project succeeding | No | Yes |
| Blocked by OI-4 consent review | No | Yes |
| Telugu quality improves in v1 | Yes — via L1 + L2 | Yes, more |
| Risk of never shipping | Low | Elevated |

Recommendation: keep L3 in v2. Model training has genuinely open-ended timelines and

a real chance of needing several iterations. Gating your first release on it risks the

platform never reaching production — and L1+L2 deliver measurable Telugu improvement in

v1 regardless.

What makes this safe is that v1 still ships FR-STT-08, FR-STT-09 and FR-STT-12 — the

self-hosted adapter, the consent-filtered export, and per-turn model attribution. L3 then

becomes configuration and training, not a retrofit. That is the difference between

"deferred" and "abandoned", and it is why those three requirements are Must in v1.

If you want L3 in v1, say so and I will re-cut the plan. It is your call and the argument for it — that Telugu quality is the product — is not unreasonable.

────────────────────────────────────────

# 9. Evaluation and Gates

| Gate | Criterion | Blocks |
| --- | --- | --- |
| S-G0 | Corpus frozen, baseline captured, targets approved | G4, all later STT work |
| S-G1 | L1 measured; WER ≤ baseline; entity accuracy improved | v1 STT sign-off |
| S-G2 | L2 measured; WER < baseline; hallucination rate acceptable | v1 STT sign-off |
| S-G3 | OI-4 consent confirmed in writing | All L3 work |
| S-G4 | L3 model beats L2 on the frozen held-out set | L3 rollout |
| S-G5 | L3 A/B on live calls at parity or better; failover proven | L3 default |

Every gate is measured on the frozen held-out set from L0. No exceptions — a model

promoted on training-set numbers is the standard failure mode of this kind of work.

────────────────────────────────────────

# 10. Risks

| ID | Risk | P | I | Score | Response |
| --- | --- | --- | --- | --- | --- |
| SR-1 | Corpus never assembled; nothing can be judged | 4 | 5 | 20 | Schedule L0 in Phase 1 as blocking; shares work with TPR-1/TPR-2 |
| SR-2 | Consent basis does not cover training (OI-4) | 3 | 5 | 15 | Start the review now; L0–L2 unaffected; if refused, L3 relies on synthetic + newly-consented audio only |
| SR-3 | Insufficient verified data volume for L3 | 3 | 4 | 12 | Synthetic augmentation; measure the volume early (NFR-STT-08 revised at L0) |
| SR-4 | Fine-tuned model beats baseline on the corpus but not on live calls | 3 | 4 | 12 | A/B rollout (FR-STT-11); live measurement, not corpus-only promotion |
| SR-5 | Corrector hallucinates entities | 3 | 4 | 12 | Minimal-edit prompting; hallucination-rate metric; store raw + corrected |
| SR-6 | Self-hosted serving hurts availability | 2 | 5 | 10 | Automatic failover to hosted (NFR-STT-07); A/B ratio starts low |
| SR-7 | Human transcription effort underestimated | 3 | 3 | 9 | Draft-then-correct; 2–3 h held-out is deliberately modest |
| SR-8 | GPU cost exceeds expectation | 2 | 3 | 6 | Rent, don't own; fine-tune, don't pre-train; E6 input |
| SR-9 | L3 slips indefinitely and the justification is never realised | 3 | 4 | 12 | v1 ships FR-STT-08/09/12 so L3 stays configuration; S-G0 targets make progress visible |

SR-1 and SR-9 are the ones to watch. Both are failure-by-postponement rather than failure-by-difficulty, and both are prevented by the same thing: doing L0 in Phase 1 and shipping the three enabling requirements in v1.

────────────────────────────────────────

# 11. Traceability

| Element | Source / target |
| --- | --- |
| §1 justification | FS-001 §3.3, §10 |
| §2 ladder | FS-001 §3.3 levels 1–3 |
| FR-STT-01…03 | TP-001 §7.2, SRS NFR-QUAL-01/02 |
| FR-STT-04 | SRS FR-PIPE-04 |
| FR-STT-05/06 | SRS FR-PIPE-05 |
| FR-STT-07 | SRS FR-PIPE-06 |
| FR-STT-08 | HLD ADR-04, LLD §1.2 |
| FR-STT-09/10 | SRS FR-DATA-06, FR-CMP-04 |
| FR-STT-12 | LLD §2.1 turn |
| §4 corpus | TP-001 TPR-1, TPR-2 |
| §7.3 governance | FS-001 OI-4 |
| §8 WBS 9 | PMP-001 §3 |
| §10 risks | PMP-001 §5 |

────────────────────────────────────────

# Appendix A — v1 obligations that keep Level 3 alive

If nothing else from this document survives scope pressure, these three must:

| ID | Requirement | Consequence if dropped |
| --- | --- | --- |
| FR-STT-08 | Self-hosted STT adapter | L3 needs new integration work, not configuration |
| FR-STT-09 | Consent-filtered training export | No corpus accumulates; L3 starts from zero whenever it starts |
| FR-STT-12 | Per-turn STT implementation and version recorded | No way to A/B or attribute quality changes |

Each is small. Together they are the difference between Level 3 being scheduled and

Level 3 being hypothetical — and Level 3 is why this platform is being built.