# Project Vaani — SDLC Document Set

Self-hosted voice AI orchestration platform (a Vapi alternative) to replace Dograh for

BS Wealth Finance's outbound Indian-language calling.

Created: 2026-08-23 · Status: Draft, awaiting sign-off at Gate G0/G1/G2

────────────────────────────────────────

# Read in this order

| # | Document | What it answers | Gate |
| --- | --- | --- | --- |
| 1 | Feasibility Study | Should we build this at all? | G0 |
| 2 | Software Requirements Specification | What must it do? | G1 |
| 3 | High-Level Design | How is it structured? | G2 |
| 4 | Low-Level Design | How is each part built? | G2 |
| 5 | Test Plan | How do we know it works? | — |
| 6 | Deployment & Operations Plan | How do we run it safely? | — |
| 7 | Project Management Plan | Who does what, when, and what could go wrong? | — |
| 8 | STT Customization Workstream | How do we actually fix Telugu speech recognition? | S-G0…S-G5 |
| 9 | Latency Engineering Plan | How do we get to sub-800ms? | L-G1…L-G6 |

Each document also exists as .docx alongside its .md.

Regenerate with python tools/md_to_docx.py.

────────────────────────────────────────

# The short version

The project is recommended. Three justifications, each decisive on its own.

Revised 2026-08-23. An earlier version of this set targeted latency parity with the incumbent. That anchored to the system being replaced instead of to the market and was wrong. Latency is now a primary goal — see justification 3 and document 9.

Architectural control. Dograh's node graph cannot make tool calls

mid-conversation, silently drops edges when saved, and can't express the nuanced

conditions sales depends on. Sales and appointment booking are structurally

impossible on it — not hard, impossible.

Speech-recognition ownership. Telugu ASR can be boosted, corrected, raced, and

ultimately fine-tuned on your own call recordings using AI4Bharat's MIT-licensed

IndicConformer. No managed platform offers this at any price, and it is the single

biggest determinant of perceived quality on these calls.

→ Planned in full in document 8.

Latency leadership. The orchestrator itself is not slow — but owning it is what

makes three decisions yours: when to stop listening, which model reasons, and

where components run. Those are worth ~1,290 ms. Target: ≤800 ms server-side,

which would lead every benchmarked commercial platform.

→ Planned in full in document 9.

────────────────────────────────────────

# Fixing Telugu STT — the four levels

| Level | What | Release | Effort |
| --- | --- | --- | --- |
| L0 | Measure — build the corpus, get a real baseline, define the entity metric | v1, Phase 1 | 9 d (≈3 net) |
| L1 | Tune — vocabulary boosting, pick the best provider on evidence | v1 | 5 d |
| L2 | Correct — fast LLM repairs the transcript; engine racing later | v1 | 5 d |
| L3 | Own — fine-tuned IndicConformer on your own call audio | v2 | 32 d |

L3 is deliberately kept out of v1 — gating your first release on a model-training

project risks never shipping, and L1+L2 improve Telugu measurably on their own. What

keeps L3 real rather than hypothetical is that v1 must ship three small requirements:

FR-STT-08 (self-hosted adapter), FR-STT-09 (consented corpus export), FR-STT-12 (per-turn

model attribution). If those slip, L3 becomes a retrofit. §8.2

sets out the alternative if you want L3 in v1 instead — your call.

────────────────────────────────────────

# Getting to 800ms — the budget

Measured reality first, because the numbers circulating are misleading. On **real phone

calls**, caller-experienced p50: Telnyx 1,296 ms · ElevenLabs 1,424 ms · Bland 1,520 ms ·

Vapi 1,558 ms · Retell 1,740 ms. Nobody is sub-second. Vendor figures run ~490 ms

lower because they measure server-side, not what the caller hears.

"100 ms" is a single-component number — Cartesia's time-to-first-audio is ~40 ms.

Voice-to-voice 100 ms is below PSTN round-trip. It does not exist.

| Component | Now | Target | Lever |
| --- | --- | --- | --- |
| End-of-speech detection | 800 ms | 250 ms | Telugu turn detector — the blocker |
| STT finalisation | 200 ms | 100 ms | Streaming partials |
| LLM → first spoken token | 600 ms | 200 ms | Non-reasoning model |
| TTS first audio | 190 ms | 190 ms | No saving available — measured floor is ~155 ms |
| Transport / queuing | 200 ms | 50 ms | Co-location in India |
| Server-side total | 1,990 ms | 790 ms | Only 10 ms under target |
| Telephony (not controllable) | +490 ms | +490 ms | Carrier physics |
| Caller experiences | ~2,480 ms | ~1,280 ms | Would rank 1st |

## ⚠ The blocker: LiveKit's turn detector doesn't support Telugu

It covers 14 languages — including Hindi, not Telugu. Silence-based endpointing can't

safely go below ~0.6 s (your callers already protested at 0.35 s), and 0.6 s alone eats

75% of an 800 ms budget. So a Telugu turn-detector model has to be trained. 19 of the

42 latency days are exactly that. Precedent exists — the same was done for Thai.

## Is 800ms actually feasible? Yes.

OpenAI's own flagship speech-to-speech model measures 820 ms end-to-end. So 800 ms

cascaded is at the frontier, not beyond it. Gemini 3.1 Flash Live measures 2.98 s.

We also checked whether a speech-to-speech model (one model, audio in → audio out, no

TTS stage) would be easier. It would not:

|  | Cascaded (chosen) | Speech-to-speech |
| --- | --- | --- |
| Latency | ~800 ms target | 820 ms (OpenAI) / 2.98 s (Gemini) |
| Telugu | Yours to train | Essentially none |
| STT ownership | Full — the whole ladder above | Gone — there is no transcript stage |
| Cost | $0.0095–$0.17/min | up to $0.30/min |
| Vendors | 5+ STT, 7+ TTS, dozens of LLMs | Two: OpenAI, Google |

Adopting S2S would mean rebuilding the platform in order to give up the exact capability

it exists to provide — and going back to per-minute pricing from one of two vendors.

Revisit if a self-hostable Telugu full-duplex model appears; Hindi-Moshi shows the

path is real.

Sequencing: the cheap wins (co-location, non-reasoning model, streaming TTS) reach

~1,200 ms with no model training at all — already better than 4 of the 5 platforms

above. The turn detector buys the last 400 ms.

Every latency target is paired with a false-interruption target. Faster endpointing

buys interruptions, and a latency win purchased with interruptions is not a win.

────────────────────────────────────────

# Scope

| v1 (non-negotiable) | Outbound calling + campaigns + STT levels 0–2 + ≤800 ms latency + live human transfer |
| --- | --- |
| v2 | Appointment booking, agent-builder UI, inbound, fine-tuned ASR (L3) |
| Never | Multi-tenancy, client logins, billing — you operate it, clients don't log in |

Stack: SIP trunk → LiveKit (WebRTC/SIP) → pluggable STT → your Brain → pluggable TTS

Estimate: ~188 engineering-days for v1, ~244 with contingency, plus 32 planned for

the v2 STT workstream. No calendar date asserted — that depends on your availability

alongside client work.

────────────────────────────────────────

# ⚠ Blocking item

Does Vobiz offer SIP trunking? Without raw audio access, nothing else matters. The

exact enquiry to send is in Feasibility Study §9.1. Costs

nothing; Plivo is the fallback; the telephony layer is designed provider-agnostic either

way.

────────────────────────────────────────

# Do these now

| # | Action | Why |
| --- | --- | --- |
| 1 | Send the Vobiz SIP enquiry | Blocks all telephony work |
| 2 | Review and sign off documents 1–4 | Opens G0–G2 |
| 3 | Gather cost inputs E1–E6 | No break-even is asserted without them |
| 4 | Start the DLT/DPDP review | Blocks go-live only, not design |
| 5 | Apply the missing `Reasoning: low` fix to Dograh WF6 | ~1.6 s win on the live system today — unrelated to this project, don't let it wait |

────────────────────────────────────────

# Two risks worth knowing about now

| Risk | Score | Note |
| --- | --- | --- |
| Telugu corpus + Dograh baseline never assembled | 20 | Has no dependencies, so it's easy to postpone — and postponing it makes both "quality parity" and every ASR improvement claim unprovable. Schedule it in Phase 1. |
| Vobiz has no SIP | 15 | One email answers it. |
| Consent doesn't cover training on your recordings | 15 | Gates Level 3 only. Start the review now; levels 0–2 are unaffected. |

────────────────────────────────────────

# Working agreement for the conversation-quality track

Recorded because it is how the current system was successfully diagnosed:

One call at a time; one change between calls

Analyse the transcript before the next call

Never trim instructions for latency — worth ~0.1 s, and objection handling is the payload.

Shortening spoken output does pay, because Telugu tokenises expensively.

Diagnose the running system before redesigning it