# Cutting Vaani per-turn latency to the 800 ms budget

# Context

Measured on real telephony (run 392, 19 turns): TOTAL 1,119 ms against a

budget of 800 ms. The client's requirement is non-negotiable, and three

behaviours that currently work must not regress: the agent answers the caller's

question first then asks its own, it answers off-topic questions, and it

remembers across turns (ask budget + repeat guard).

The client also asked specifically for semantic turn detection — audio and

text combined, with the LLM thinking before the caller has finished. Pipecat

ships exactly that and we are not using it.

## Two corrections to what was previously reported to the client

1. Prompt size does NOT cause MB Solar's extra 600 ms. I reported a

correlation across the five agents (1,890 chars → 1.45 s, 9,811 → 2.06 s).

dograh-vapi/findings.md §F6 already ran this as a controlled experiment —

every tier cache-warmed, round-robin interleaved, 7 rounds — and found the

across-tier effect (0.339 s) sits inside the within-tier noise floor

(0.786 s), with reasoning output flat (~110 chars) at every prompt size. My

comparison was uncontrolled and is the same cache-warmth artefact. **Trimming

prompts is cancelled**, which also preserves the standing rule that objection

handling is the payload.

2. The agent does NOT already stream speech — the client was right.

I said streaming was already working. It is not. service_factory.py:618 passes

text_aggregation_mode=TextAggregationMode.TOKEN to Deepgram, with a comment

whose reasoning is written about Cartesia. The live Cartesia branch at

service_factory.py:697 does not pass it. Pipecat's own Cartesia docstring:

*"we aggregate sentences before sending to TTS. This adds ~200-300ms of latency

per sentence… TODO: Consider making TOKEN the default for Cartesia in 1.0."*

Worse for us: the sentence aggregator needs a non-whitespace character after

terminal punctuation, and our replies are typically one sentence ending in a

question mark — so the TTS receives nothing until the LLM has finished the whole

reply. The measured "TTS 69 ms" is clocked after that wait, which is why it

looked free.

────────────────────────────────────────

# Phase 0 — Ship the safe wins now (client's chosen sequencing)

Three changes, none touching the turn decision, so none can raise the

false-interruption rate.

## 0a. Kill a 250 ms dead timer — config only

stt_finalisation_budget_secs: 0.45 → 0.2 (schema floor is ge=0.2) on all five

workflows via bswealthfinance/tools/sync_latency_config.py.

With turn_wait_for_transcript=False this value no longer gates waiting for a

final. What it still does: when the late final arrives,

turn_analyzer_user_turn_stop_strategy.py:302 arms

max(0, stt_timeout − stop_secs) = 0.25 s of dead wait before

push_aggregation() emits the context frame. SarvamSTTService never sets

TranscriptionFrame.finalized, so the fast branch cannot short-circuit it.

Saving: exactly 250 ms on every late-final turn. Revert is one command.

## 0b. Stream tokens to Cartesia — the client's own "speak while generating"

Add stream_tokens to create_tts_service (mirror the existing

stt_finalisation_budget_secs parameter pattern at service_factory.py:264),

thread it from run_configs at run_pipeline.py:784, pass

text_aggregation_mode=TextAggregationMode.TOKEN into the Cartesia branch

(service_factory.py:697). Default False in

api/schemas/workflow_configurations.py; enable per workflow.

Saving: 100–400 ms, largest on single-sentence replies, which is most of ours.

ReplySanitizer.HOLDBACK = 24 means the first chunk is already ~24 characters,

so the opening is not synthesised letter-by-letter, and Cartesia keeps prosody

context across the websocket stream.

Rollout: MB Solar only, listen to one test call, then the other four. No test

can judge Telugu prosody — only an ear. (Assumption, since the client did not

pick a rollout option; the one-command revert makes this safe.)

## 0c. llm_hedge: 2 → 3 — config only

Code default is already 3 (workflow_configurations.py:127); all five stored

configs say 2 and stored config wins. In-repo bench: hedge-2 p50 0.653 / p90

0.761 vs hedge-3 p50 0.325 / p90 0.405.

Be sceptical: one bench, one prompt, one afternoon, against a documented

0.256–1.161 s within-request spread. Expect 100–250 ms with wide bars. Do

not run this concurrently with Phase 3 speculation — hedge-3 × speculation is up

to 6 concurrent generations per turn, and run 92 lost a call to less than that.

────────────────────────────────────────

# Phase 1 — Measurement, in parallel with Phase 0

The 523 ms "endpoint" is a residual (total − llm_ttfb − tts_ttfb), not a

measured quantity. It hides at least: VAD 200 ms, analyzer wait, STT

finalisation after the verdict, the 250 ms timer from 0a, and TTS sentence

aggregation from 0b.

`tools/vaani_runs.py::decompose` — also read rtf-latency-breakdown; print

the per-turn distribution, not the mean. Late-final turns cluster near

0.8–1.0 s; that cluster's size is the multiplier on 0a's and Phase 2's savings.

`run_pipeline.py:1391-1415` — add text_aggregation_secs to the payload.

Pipecat already computes it (user_bot_latency_observer.py:83-92) and we throw

it away. That field is 0b's saving, measured.

Cross-check against tools/true_latency.py, which measures from the separated

user.wav/bot.wav and owes nothing to the logs.

────────────────────────────────────────

# Phase 2 — Semantic turn detection (the client's explicit request)

## What we have now

TeluguTurnAnalyzer is already a hybrid detector: audio prosody (f0 track,

1.5 s tail) plus text via TextAwareTurnStopStrategy.note_text() and

completeness.sounds_unfinished(). It ends 33.9–43.9% of turns early at under a

2% false-cutoff rate. It exists because **no vendor turn detector supports

Telugu** — Smart Turn v3 covers 23 languages, LiveKit 14, Deepgram Flux 10.

The text half is a heuristic, not a model. That is the gap.

## 2a. Switch STT to saaras:v3-realtime — prerequisite for everything below

Config only; routing already exists (service_factory.py:432-436). Measured

speech-end→transcript 0.373 s (saarika:v2.5) vs 0.091–0.121 s (realtime).

Critically, saarika:v2.5 emits no `InterimTranscriptionFrame` at all, which

is why partial-response and speculation are inert today. No partials = no

semantic turn detection is possible.

Gate this on transcript accuracy, not latency: stream_type="fast" is

Sarvam's least stable, and a documented pair read "yes yes yes" as partial and

"no no no, I don't have" as final. Compare field-capture rate over ≥3 calls each

way before keeping it.

## 2b. Fix two latent outages that 2a would arm — MUST precede 2a going live

`partial_response.py` direction bug (confirmed, not suspected).

UserStoppedSpeakingFrame is broadcast from the aggregator

(llm_response_universal.py:1290), and broadcast_frame pushes one copy

upstream. PartialResponder sits before the aggregator, so the only copy

it sees is upstream, and it re-pushes the promoted transcript in that same

direction — toward the STT, never reaching the LLM. It also sets _promoted,

which suppresses the genuine final. With interims on, that is a turn where

the agent gets no text and says nothing. All six tests use DOWNSTREAM, the

direction that never occurs live. Fix: push DOWNSTREAM unconditionally; add a

test driving UPSTREAM. **Keep the existing "only promote if no final in hand"

trigger** — do not promote at VAD-stop until a hit-rate measurement exists.

Speculation would generate from the wrong prompt.

run_pipeline.py:249 builds the speculative prompt from

compose_system_prompt_for_node, not compile_vaani_system_prompt, and

:263 passes get_state_block=lambda: "". **The state block is where all

three protected behaviours live** — answer-first, MAX_ASKS_PER_FIELD, the

repeat guard. A speculation hit would speak a reply with none of them.

Set speculation_enabled: false in stored config on all five workflows before

2a, and add a test asserting the speculative system prompt is byte-identical to

the installed one with a non-empty state block.

## 2c. Adopt pipecat's LLM turn-completion protocol

pipecat/src/pipecat/turns/user_stop/llm_turn_completion_user_turn_stop_strategy.py

is precisely the architecture in the client's transcript: the LLM is polled on

partial input and emits a marker instead of a reply —

✓ complete → speak; ○ incomplete-short → wait; ◐ incomplete-long → wait —

so the model is thinking while the caller is still speaking and the response is

ready the moment the turn ends. Config lives in UserTurnCompletionConfig

(instructions, incomplete_short_timeout 5 s, incomplete_long_timeout 10 s).

It installs alongside deferred(...)-wrapped detector strategies, so

`TeluguTurnAnalyzer` keeps its authority over the audio half and the LLM

supplies the semantic half — audio + text, which is exactly the transcript's

recommendation.

Two integration risks that must be settled first:

Marker protocol vs `MODE_PROTOCOL`. Our compiler already requires the

first line of every reply to be MODE: ASK|CLOSE (compiler.py:270). Two

protocols both claiming the first token will collide. Decide whether the mode

line moves, or the completion instructions are rewritten to co-exist.

State-block staleness. Polling mid-utterance renders the state block

against text the caller has not finished. SpeculationProbe currently sits

before StateInjector in vaani/pipeline.py, so it would see the

transcript before triage refreshes state. The trigger must move after

StateInjector (or be called from StateInjector.note_user_text after

_refresh()).

**Expected: up to the full 527 ms LLM TTFB on turns where the verdict lands

after the transcript.** Verify with rtf-speculation hit rate and llm_secs

going to ~0 on hits. **Acceptance gate: run tools/vaani_eval.py with completion

forced on every turn and require byte-identical replies to the non-semantic

path.** If they differ, the state assembly is not identical and it is not ready.

## 2d. Throttle the detector's CPU — last, smallest

TeluguTurnAnalyzer._probability() costs ~5–7 ms and runs **synchronously on the

event loop** on every 20 ms frame once silence starts — ~10 calls (53 ms) at a

523 ms endpoint, up to ~54 (286 ms) at endpoint_max_secs 1.40 s. Score every

3rd frame instead. _last_probability becomes ≤40 ms stale against a

300–1,400 ms wait. This is mostly a concurrency win, not a p50 win — do not

claim a median saving without measuring one. A coarser cadence can only delay a

COMPLETE, never advance it, so it cannot raise false interruptions.

────────────────────────────────────────

# Explicitly NOT doing, and why

Trim prompts / two-tier prompts — §F6 ran the controlled experiment and

cancelled it. Effect inside noise.

Lower VAD `stop_secs`, `smart_turn_stop_secs`, or `endpoint_min_secs` —

the recorded sweep shows deciding 0.10 s earlier moved early-ended turns

33.2%→21.1% and mean endpoint up 0.718→0.753 s. **Deciding sooner makes calls

slower**, and spends directly against the 2% false-interruption floor.

Move vendors to India — already there: Groq 30.8 ms, Cartesia 21.1 ms,

Sarvam 37.8 ms RTT.

Add prompt caching — already working (97.5% measured); prewarm.py warms

the prefix during the greeting.

A non-reasoning model — reasoning_effort:"none" is rejected by Groq for

gpt-oss; low is the floor, and this account has no non-reasoning alternative.

Reinforcement learning for latency — RL changes word choice; it cannot make

the system notice a caller stopped talking. The 3,810 harvested examples are

worth using for quality (distillation/SFT), separately.

`turn_start_min_words` / `provisional_vad_pause_secs` — dead config while

turn_start_strategy = "default".

────────────────────────────────────────

# Expected outcome

|  | now | after |
| --- | --- | --- |
| 250 ms dead timer (0a) | 250 | 0 |
| TTS sentence buffering (0b) | 100–400 | ~0 |
| LLM hedge (0c) | — | −100…−250 |
| STT finalisation (2a) | ~373 | ~110 |
| LLM overlapped (2c) | 527 | →0 on hit turns |

Server-side p50 should land inside the 800 ms budget. The caller hears that

plus telephony_overhead_ms: 490, which latency_budget.yaml marks *"NOT

engineerable" — so ~1.0 s at the caller's ear is the floor*, and I will

report the real number rather than the target.

────────────────────────────────────────

# Verification (every phase, same method)

python tools/vaani_runs.py --workflow N --run <id> — per-turn

endpoint/LLM/TTS decomposition from rtf-latency-breakdown.

python tools/latency_timeline.py — trend across agents and dates.

python tools/vaani_probe.py --workflow N --script derail|website|interrupt|silly

— the behaviour scripts, on all five agents, before and after.

python tools/vaani_eval.py --workflow 2 — twice, because the noise band

is ±3 cases; a single run proves nothing.

Offline suite: `python -m pytest api/tests/test_vaani_*.py test_coach.py

test_speech_register.py test_layers_are_reusable.py --noconftest` — currently

402 pass, 10 pre-existing failures in test_vaani_filler_cover. Diff the

failure list before/after; zero new failures is the gate.

After each deploy: curl api + ui, and confirm the Coolify

docker_compose_domains ports are intact (the cause of the 4 Sep outage).

Regression guards to add: a sync_latency_config assertion that stored config

and code defaults agree (this class of "shipped change never ran" caused 0c); a

test_cartesia_tts_service_factory assertion for the aggregation mode; an

UPSTREAM-direction test for PartialResponder.